## Sheet1
H&VV Meetings | Key Dates |  |  |  |  | NEWS ITEM
IAE | 29th Jan | Logo design/Competition Design | Organising Group | Date | IAE (Inclusiveness & Engagement)
Organising Group | 5th Feb | Logo, postcard, approval
News Items* | 19th Feb | Database, Communities, Volunteers | Matthew's & David Rowson | 29th Jan | Design of Postcard
| 20th Feb | Post card delivery starts/School competition Starts*
| 5th March |  |  |  | Design School Competition, free publicity date/delivery/data handling/outline of plan
| 19th March | Finalize Pop up Shop * | Approval of Postcard | 5th H&VV Meeting | Approval of Postcard
| 27th March | Pop up shops opens | Data Handling Design for responses from Postcard/Survey Monkey | 6-12th Feb Printing of Postcard | Printing of Postcard | Email Chamber of Commerce for Raffel Prizes for the Haslemere and Villages Launch Day let them know about launch day - Design Localism Statement and Vission
| 2nd April 16th April 8th/15th April | Private Viewing * | Volunteer Contact Point, news writting, Promotional material, Leaflets for Pop up Shops & Launch day |  |  | Website up and running, drop boxes, free publicity in local publications dates? Article in Haslemere Herald, Visit other Community arranged events
| 27th April | Launch *
|  |  | Drop boxes, Haslemere Hall, Nobbs, Waitrose, Coop, Tesco, Hazelway, Website with survey (same as postcard), | 13th February | Delivery of Postcard * News Item
|  |  |  | 19th February H&VV Meeting | Create Data base of community interest groups, commerce contacts. Identify attendees for 27th April.
|  |  |  | 20th Feb | Inform schools about photo competiton - flyer, prizes, email address, after 28th February
28th Feb
|  |  |  | 5th March H&VV Meeting | Design Pop up Shops
|  |  | Design Pop up boards for shop, Speakers Confirmed |  | Speakers Confirmed
|  |  | Finalises Volunteer Plan for Pop up Shop & Timings of Shop | 19th March H&VV Meeting | Finalises Volunteer Plan for Pop up Shop
|  |  | Pop up Shop Opens | 27th March | Pop up Shop Opens*New Item about Pop up shop launch
|  |  | Volunteers needed for refreshments, Sign posting to Launch, Ambassadors, Film of Old Haslemere (David O'Brein), Recorded voice speaking about what Localism can do for our town, Guest speakers, Kids activities (play dough/Lego? Leaflet distribution | 2nd April H&VV Meeting | Refreshment Coordinated, volunteers, Group to design kids activities, Design meeting for Launch IAE Group. Arrange Private Viewing of Localism Video,Pictures of Old Haslemere & Vision | Private Viewing/invite groups/Villages/Press/Location?Date?
|  |  | Finalises Judges for the Launch Day | 9th April H&VV Meeting | Finalise Launch Agenda * News Item
16th April H&VV Meeting
|  |  |  | 23rd April H&VV Meeting | Finalise Refreshments
|  |  | Judging of the competition/Speakers/Announce Phase 2 | 27th April LAUNCH DATE
Phase 2
|  |  | Collate Data from Phase 1 i.e Post card & Online Survey |  | Review/Evaluation
Business Breakfast for Haslemere Chamber of Commerce
Notes of the Inclusiveness and Engagement Meeting held at 15 Lower Street, Haslemere on Thursday, 17th January 2013 at 09.30
Present: Ann Finlayson, Victoria Leake
Apologies: Clive Rollinson, Marion Meecham, Jane Chandler, Lesley Banfield, Nikki Barton, Maria Mateo,